# PRE-WORKSHOP SUGGESTED ONLINE MEETING SCHEDULE

This is a suggested schedule for pre-workshop meetings with a core team. These are flexible and depending on time available can be combined or separated into fewer or greater number of meetings.

| Meeting | Topics and key questions | Pre-session preparation | End of meeting Goals | Post meeting actions |
| --- | --- | --- | --- | --- |
| 1. | Scope, aims and structure of planning project - Introduction to CPSG, our process (principles, steps, etc.) and how a workshop will run - Discussion & confirmation of species scope (if multi-species project, can include examples of groupings options) - Develop a statement explaining the situation and pathway through which the planning initiative will lead to change - Agree desired outputs (ie. Report type) - Discuss workshop format (number of meetings, online or in-person, date, venue, etc.) - Determine the need for translation/translators at workshop - Discuss responsibility and framework for plan implementation (agree whether determining this will be part of the planning process) - IF time: can introduce idea and start to think about what main threats might be, and who has an impact on the conservation of the species (stakeholders) | - PowerPoint presentation | - The core team should understand the workshop process - The facilitator should have an idea for what tools, info and steps will be necessary, how the workshop will be structured, and what the outputs will be - Both core team and facilitator should know what the output of the project will be | - Have core team share species list if they have it (or ID if it needs to be completed) - Preliminary participant list could be shared if it was discussed in meeting |
| 2. | Likely key issues and tools agreed - Confirm scope discussed in previous meeting - ID key threats (and their drivers) the species - Discuss what might be the main obstacles to addressing them, and what opportunities might exist (ex-situ, ongoing projects, etc.) - ID if these differ across species, areas, etc. - Discuss and ID tools needed (PVA, WDRA, ex-situ, etc.) - ID & prioritise stakeholders that should be invited to workshop - Discuss possible working groups based on the species, stakeholders, and threats (consider any existing data such as redlists, that might help with this decision) | - Review any red list data available for the species to gain background knowledge on species, threats, etc. - PowerPoint presentation - Can use platform like Mural to brainstorm and discuss themes | - Team including facilitator should understand preliminary threats, obstacles, opportunities, ongoing actions, stakeholders and possible working groups | - Compile any existing literature or outputs from previous project: review for additional background knowledge and if any of this can/should be included in briefing materials - Once stakeholders are identified, a participant list and official invitations can be drafted and prepared to be sent out - Draft agenda can start to be assembled and shared (if not already) |
| 3. | Logistics: Agenda and Invitations - Agenda should be reviewed and finalised, including ID of keynote speakers for opening address and presenters for scene-setting presentations - Confirm any details not yet agreed on (invitations, working group themes, species list, etc.) - Confirm workshop materials (room, projector, flip charts, etc.) - Discuss any additional logistics, such as travel costs and accommodation for participants, letter from agencies or governments needed, field trips, etc. | - As needed | - All team should understand what is needed and responsibilities for next steps for workshop logistics | - Invitations are sent out (if not already) - Scene-setting presentations are selected and presenters ID’d - Any additional logistics can be confirmed through email exchanges |
| 4. | Logistics & Briefing Materials: - Confirm any logistics not yet finalized (agenda, invitations, participant list) - Discuss briefing materials: what should be included, the format they will be shared (ex. Email, website), and who will develop them. | - Compile any existing species data (ex. Red list, previous reports, etc.) in a simple and appealing way (ex. Maps, tables, etc.) that could be understood by participants - Compile additional documents that could be used for briefing materials | - Identify all briefing materials needed and who will be responsible for sharing them, and how they will be shared with all participants in advance of the workshop | - Assemble typical briefing materials plus any additional identified by team, ex: - Workshop Agenda - Into to CPSG planning process - Species list - Previous reports/Red list data (and description of red list categories if needed) - Maps highlighting area(s) of interest - Grant background information - Share briefing materials with all participants |
| Additional Meetings (as needed) | - Meet with any facilitators/local participants for training or run through of workshop process | As needed | As needed | NA |
| POST-Workshop meetings | As needed: - To review draft and final report/outputs (can be done through email as well) - To deliver any additional responsibilities outlined in project or grant | As needed | As needed | NA |